## Sheet1
Task ID | Task Name | Owner | Start Day | Duration (Days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | Project Planning & Requirements Review | Eraka & Charles | 1 | 2 | bar: 1 to 2
2 | Design User Interface (Wireframes) | Charles | 3 | 3 | bar: 3 to 5
3 | Set Up Development Environment | Charles | 3 | 2 | bar: 3 to 4
4 | Develop User Registration | Charles | 6 | 3 | bar: 6 to 8
5 | Develop User Login & Authentication | Charles | 9 | 3 | bar: 9 to 11
6 | Develop User Profile Management | Charles | 12 | 3 | bar: 12 to 14
7 | Develop Movie Search Feature | Charles | 6 | 4 | bar: 6 to 9
8 | Integrate Streaming Service APIs | Charles | 10 | 5 | bar: 10 to 14
9 | Develop Subscription Management | Charles | 12 | 4 | bar: 12 to 15
10 | Develop Watchlist Feature | Charles | 15 | 3 | bar: 15 to 17
11 | Develop Ratings & Reviews | Charles | 15 | 3 | bar: 15 to 17
12 | Develop Recommendation Engine | Charles | 16 | 4 | bar: 16 to 19
13 | Develop Notifications | Charles | 15 | 2 | bar: 15 to 16
14 | System Integration Testing | Both | 21 | 3 | bar: 21 to 23
15 | Bug Fixes & Quality Assurance | Both | 24 | 2 | bar: 24 to 25
16 | Final Review & Deployment Preparation | Both | 26 | 2 | bar: 26 to 27