## Slide 1
EZTechMovie StreamList
Week 2 Program Design
Gantt Chart and Application Wireframes
Movie Search
Streaming Availability
Watchlist
Subscription
Charles Trayes Jr. | Eraka Russell
The University of Arizona Global Campus | August 2026
Goal: turn the original StreamList concept into an all-in-one monthly movie discovery and streaming access service.

## Slide 2
Project Gantt Chart
Tasks come directly from the SRS and are sequenced by dependency. Some work can run in parallel.
Task / estimate
Week 1
Week 2
Week 3
Week 4
Week 5
Finalize SRS and scope | 1 day
Both
Create Gantt chart and wireframes | 2 days
Charles
Set up shared repo and app architecture | 1 day
Both
Account login and secure authentication | 2 days
Eraka
Movie search and metadata API | 3 days
Charles
Movie details and streaming availability | 3 days
Both
Watchlist, favorites, ratings | 2 days
Charles
Subscription and payment workflow | 3 days
Eraka
Accessibility, security, error handling | 2 days
Both
Integration and usability testing | 3 days
Both
Final status report and presentation | 2 days
Both
Key dependency: streaming availability depends on movie search and metadata. Payment work can run alongside watchlist development. Testing follows feature integration.

## Slide 3
User Flow and Navigation
The flow keeps the main task simple: search for a movie, see where it is available, then watch or save it.
Home
Search
Search
Results
Movie
Details
Streaming
Options
Open Provider
or Stream
Add to
Watchlist
Compare Rent /
Buy Options
Sign In /
Subscribe
Primary navigation
Home
Search
Watchlist
Recommendations
Account
Wireframes stay low fidelity on purpose. They show structure, element placement, hierarchy, and movement between screens without locking the team into final colors or branding.

## Slide 4
Wireframe 1: Home and Movie Search
Low-fidelity desktop layout for the main discovery workflow.
STREAMLIST
Home Search Watchlist Account
Search movie, actor, director, or genre
SEARCH
Popular this week
MOVIE
POSTER
Movie title
Genre • Year
MOVIE
POSTER
Movie title
Genre • Year
MOVIE
POSTER
Movie title
Genre • Year
Home
Search
Watchlist
Account
What this screen supports
• One search field is the main action.
• Users can search by title, actor, director, genre, year, or keyword.
• Movie cards show enough detail to choose the next step without clutter.
• Persistent navigation gives fast access to saved movies and account tools.
• The layout can collapse to one column on mobile devices.
Design reference: Springboard recommends mapping user flow first, then sketching the layout, hierarchy, buttons, navigation, and static elements before visual polish.

## Slide 5
Wireframe 2: Movie Details and Streaming Options
This screen answers the user’s main question: Where can I watch this movie?
STREAMLIST
POSTER
Movie Title
2026 • PG-13 • 2h 8m
Genre | Director | Key cast
Short movie description goes here.
+ WATCHLIST
★ FAVORITE
Where to watch
Provider A
Included
OPEN
Provider B
$3.99 rent
OPEN
Provider C
$9.99 buy
OPEN
Functional behavior
Availability
Show supported subscription, rental, purchase, and free options.
Provider action
Open the approved provider or use direct playback only when authorized.
Price comparison
Let users compare rent and purchase options before leaving StreamList.
Watchlist
Save the title so the user can return later or receive an availability alert.
Fallback
If provider data fails, show a clear unavailable message instead of stale results.

## Slide 6
Wireframe 3 and Design Summary
The final screens support retention, subscriptions, privacy, and user control.
WATCHLIST
Search saved movies
POSTER
Movie title
Provider • Status
⋯
POSTER
Movie title
Provider • Status
⋯
POSTER
Movie title
Provider • Status
⋯
POSTER
Movie title
Provider • Status
⋯
Home
Search
Saved
ACCOUNT
Profile
Subscription plan
Payment method
Connected services
Notifications
Privacy & security
Sign out
MANAGE SUBSCRIPTION
How the design supports the project
Clear roadmap
The Gantt chart sequences work, shows dependencies, and identifies tasks that can run together.
Focused wireframes
Each screen has one main purpose and shows element placement before coding begins.
Scalable structure
Search, streaming availability, watchlists, subscriptions, and account features can grow as separate modules.
Security first
Authentication, payment handling, privacy controls, and testing are planned before final release.
Next step
Review the wireframes with the team, revise them, then implement the approved flow in React.
GitHub: https://github.com/charlestrayesjr/streamlist
GitHub: https://github.com/erakarussell/streamlist